## Instructions
3-Week Lookahead Starter Template
How to use this file:
1. Go to the '3-Week Lookahead' tab.
2. Fill in the 'Week of' date at the top.
3. Blue text marks cells meant to be edited. Replace the example row (row 6) with your own activities, then delete it or keep it as a reference and add rows below.
4. The daily columns under WEEK 1 are for a quick status mark per day (e.g. an 'x', a percentage, or a short note). Use whatever convention your team already uses.
5. WEEK 2 and WEEK 3 columns are for the planned activity for that week at a glance, not a daily breakdown.
6. 'Days Remaining' calculates automatically from the Planned Finish date, so leave that column's formula alone.
This is a manual, P6-independent template. Nothing here reads or writes P6 files.

## 3-Week Lookahead
3-WEEK LOOKAHEAD | [5 empty] | Week of: | FILL IN
Act. ID | Activity Description | Area / Location | Responsible | Planned Start | Planned Finish | WEEK 1 (THIS WEEK) | [5 empty] | Week 2 Plan | Week 3 Plan | Predecessor / Constraint | Days Remaining | Notes
[6 empty] | Mon | Tue | Wed | Thu | Fri | Sat
EXAMPLE ROW: replace with your own data, or delete
A1010 | Form and pour footings - Grid A-C | Area 2 | J. Smith | 2026-08-03 | 2026-08-07 | x | x | x |  |  |  | Strip forms, begin backfill | Set anchor bolts | Concrete cure 3 days (FS+3) |  | Inspector booked for Fri AM
CPM Toolkit ¦ 3-Week Lookahead Starter Template ¦ v1.0
Formulas:
Days Remaining = IF([Planned Finish]<>"",[Planned Finish]-TODAY(),"")