## Instructions
Schedule Risk & Contingency Starter Kit
What this is:
A 3-point (PERT) estimating workbook. For each activity or risk item, enter an Optimistic, Most Likely, and Pessimistic duration. The sheet calculates a PERT-weighted expected duration and a standard deviation per item, then combines them into a project-level expected duration and a P50 / P80 / P90 range.
What this is not:
This is not a full Monte Carlo simulation. It doesn't model correlations between activities or run thousands of iterations. It's the standard lightweight alternative: fast to build, transparent, and good enough to put a number on contingency for most schedules. For a full simulation on a complex or high-value schedule, that's still worth doing separately.
How to use it:
1. Go to the 'Risk Register' tab.
2. Blue text marks cells meant to be edited. Row 5 is an example, replace it with your own items.
3. List either individual activities or risk-bearing groups of activities, whichever gives you a more manageable list. 15-30 items is a normal range.
4. The bottom summary combines every row into a project-level Expected, P80, and P90 duration.
5. '% of Total Variance' ranks which items are driving the uncertainty; the top few are worth managing first.

## Risk Register
SCHEDULE RISK & CONTINGENCY (3-POINT / PERT)
Item / Activity | Optimistic (O) | Most Likely (M) | Pessimistic (P) | PERT Expected (Te) | Std Dev (SD) | Variance | % of Total Variance
EXAMPLE ROW: replace with your own items. Durations in working days.
Excavation - unexpected groundwater | 5 | 8 | 20
Sum of variance (used above):
PROJECT SUMMARY
Expected duration (P50), sum of Te:
Combined std dev (independent items):
P80 duration (P50 + 0.84 SD):
P90 duration (P50 + 1.28 SD):
Suggested contingency (P80 minus P50):