## Checklist
SCHEDULE HEALTH CHECKLIST
Mark each item Pass / Flag / N-A as you review. Status column has a dropdown.
# | Check | What to look for | Status | Notes
1 | Logic completeness | Every activity has at least one predecessor and one successor, except the true start and finish milestones.
2 | Leads (negative lag) | No relationship uses a negative lag to fake an overlap that isn't real logic.
3 | Excessive lag | Long positive lags are actual waiting time (cure, cool-down, approval), not a placeholder for missing logic.
4 | Relationship types | The large majority of relationships are Finish-to-Start. Start-to-Start and Finish-to-Finish pairs are used deliberately, not as a shortcut.
5 | Hard constraints | Mandatory or 'must finish on' constraints are rare and each one is justified (contract date, regulatory date, etc.), not used to force a date.
6 | High float | Activities carrying unusually high total float are checked: is that float real, or is a missing successor hiding it?
7 | Negative float | Nothing on the schedule is showing negative float without an explanation already in hand.
8 | Long-duration activities | No single activity runs longer than about 44 working days without being broken into trackable pieces.
9 | Invalid or out-of-window dates | Actual dates make sense against status (no actual start on a not-started activity; no missing actual finish on a completed one).
10 | Data date currency | The schedule's data date is current for this reporting period, not stale from a prior update.
11 | Out-of-sequence progress | Activities aren't shown progressing before their predecessors finish without a documented reason.
12 | Critical path sanity | The critical path tells a story that makes sense to someone who knows the project, not a path that jumps around illogically.
13 | Calendar assignment | Activities are on the calendar that matches how the work actually happens (5-day, 6-day, weather, cure, etc.).
14 | Milestone naming | Contract and key milestones are named and coded consistently so they're easy to find and report on.
Passed:
Flagged:
CPM Toolkit ¦ Schedule Health Checklist ¦ v1.0